## Instructions
What is an Attitude Influence Map?
• A graphical scatter plot that identifies a project's supporters and detractors
• Plots each individual's attitude toward the project and their level of influence based on seniority, intellect or knowledge
• The bubble sizes measure how difficult it may be to influence the individual and change their position
• This is not a process for a large number of proejct team members: keep it to at least two other people to get a balanced view
Which Business Problems Does the Tool Solve?
• Quickly identifies individuals who may threaten the success of your project
• Applied early in the process, allows proactive management of detractors to address their concerns without need to escalate the problem through management hierarchy.
• May help turn detractors into supporters
Benefits:
· Provides a visual political map to clarify the landscape around your team
· Pinpoints blocking managers who can disrupt your project
· Helps you do something about it before it affects the project
· Encourages you to consider the project environment
How to Apply the Tool:
Step 1: Generate a list of those who might impact your program
Step 2: Plot them against the two axes (Attitude and Influence) by providing the following information for each person:
a. Attitude (horizontal axis) – Rank the person’s attitude. Start by identifying the most negative and most positive persons. Then as you populate the chart, you can gauge comparisons against the two extremes.
b. Influence (vertical axis) – Rank the person’s influence. Often it is their position in the organization, but think also of those individuals at the lower levels of the organization who have a high amount of influence.
c. Percent chance of influencing their position - A larger bubble means that it will be more difficult for you to influence them. Percentages can be estimated with a similar comparison process used for estimating 'Attitude' and 'Influence'.
Step 3: Look at the quadrant of high influence and negative attitude to focus your efforts and work on those individuals who are most likely to threaten your success.

## Attitude_Influence
How to Apply the Tool:
Step 1: Generate a list of those who might impact your program
Step 2: Plot them against the two axes (Attitude and Influence) by providing the following information for each person:
a. Attitude (horizontal axis) – Rank the person’s attitude. Start by identifying the most negative and most persons. Then as you populate the chart, you can gauge comparisons against the two extremes.
b. Influence (vertical axis) – Rank the person’s influence. Often it is their position in the organization, but think also of those individuals at the lower levels of the organization who have a high amount of influence.
c. Often pair-wise comparisons are helpful to understand
Step 3: Look at the quadrant of high influence and negative attitude to focus your efforts and work on those individuals who are most likely to threaten your success. Devise specific remedies for each individual (1:1's, working with their associates, and even consider talking to their boss as a last resort.
| Person | Attitude | Influence
| Mary, Ops | 0 | 6.5
| Fred, Eng | 4 | 4
| Jill, Mkt | 3 | 8
| Betty, Sales | -4 | 8
| Bill, QA | -2 | 3
| Bob, UX | -3 | 7
| Sarah, IT | -4 | 9
| Mandy, Finance | -4.5 | 4
Influence
Attitude
High Influence, Negative Attiitude

## Graphics
Person | Attitude | Influence
Mary, Ops | 0 | 6.5
Fred, Eng | 4 | 4
Jill, Mkt | 3 | 8
Betty, Sales | -4 | 8
Bill, QA | -2 | 3
Bob, UX | -3 | 7
Sarah, IT | -4 | 9
Mandy, Finance | -4.5 | 4
Influence
Attitude
High Influence, Negative Attiitude