## Instructions
What is a Deliverable Hit Rate Chart?
• The chart monitors the progress of completed tasks against a target over time.
• Best applied to complex programs with a large number of tasks, it is a high-level graphical representation that indicates if the rate of task completion is on track for delivering the program on time.
Which Business Problems Does the Tool Solve?
• Shows true work accomplished versus plan.
• Makes software development progress visible.
Benefits:
• The Deliverable Hit Rate Chart is a high-level snapshot that indicates whether or not a large program is on track for an on-time delivery
• The tool is easy to construct and provides an early warning when the team is not executing to the target number of tasks, thus driving corrective action to get the team back on track
• It is an elegant solution for communicating a large amount of data in an easy-to-interpret graphical representation
How to Apply the Tool:
• Vertical axis defines the total number of tasks that are tracked in the project.
• Horizontal axis is a function of time as defined by the project schedule.
• Shows the contrast between the targeted and the actual rates of completed tasks.
• Create a Deliverable Hit Rate Chart with your team.

## Deliverable Hit Rate
Month | Target Hit Rate | Actual Hit Rate
Sept | 0 | 0
Oct | 100 | 100
Nov | 200 | 200
Dec | 300 | 350
Jan | 400 | 375
Feb | 500 | 425
Mar | 600 | 485
Apr | 700 | 550
May | 800 | 650
June | 900
July | 1000
How to Apply the Tool: • Vertical axis defines the total number of tasks that are tracked in the project. • Horizontal axis is a function of time as defined by the project schedule.
• Shows the contrast between the targeted and the actual rates of completed tasks. • Create a Deliverable Hit Rate Chart with your team