## Instructions
What is a Function Phase Matrix?
• A way to identify project objectives, roles and responsibilities, and key deliverables across all phases of a project.
• A table organized by key functions (rows) and project phases (columns), showing required activities for each phase.
• This tool allows you to visually identify dependencies between team members and milestone deliverables.
Which Business Problems Does the Tool Solve?
• This tool increases the effectiveness of a project team by clarifying roles and responsibilities early in the life of a project.
• Accelerates the ramp up of new hires by highlighting responsibilites with no owners early in the process.
Benefits:
· Ensures that you have cross-functional alignment at the phase/milestone level
· Ensures you have all key deliverables assigned to individuals
· Is a scalable tool you can apply to large or small teams, simple or complex projects, and local or globally dispersed teams
· Helps you align your team with product and delivery expectations when you use it in management reviews
How to Apply the Tool:
Use the below instructions to create your own Function Phase Matrix using the Sample on the 'Function_Phase' tab as a starting point.
Step 1: Rows represent key functions. Columns represent project phases
Step 2: Identify roles and responsibilities of team members.
Step 3: Identify and assign expected deliverables.
Step 4: Identify potential gaps and overlaps.
Work Session Steps:
• Break into teams to allow cross-disciplinary discussion
• Use sample provided provided on the 'Function_Phase' tab to create a Function Phase Matrix
• Identify key functions of team members
• Identify major project phases
• Clarify key deliverables
• Identify/assign deliverables expected from new hires
• Identify potential gaps and overlaps

## Function_Phase
Function |  | Concept |  | Concept Review | Investigation |  | Product Proposal Review | Design | [5 empty] | Design Maturity Review | Validation |  | Production |  | Post Mortem Review
| Purpose of Phase | Exploring technical and market possibilities to meet customer needs. |  |  | Formulate boundary conditions of project; proof of concept; prototype or simulation completed |  |  | Engineering Validation Testing (EVT): Complete detailed product design conforming to specifications | [6 empty] | Design Validation Testing (DVT), Process Validation Testing (PVT): Prove Design Integrity and Manufacturing Process by testing units built in a production environment. |  | Satisfy customer demand, respond to customer problems, meet revenue commitments and achieve mfg goals
[8 empty] | Pre EVT |  | EVT 1.2. |  | EVT Final
| Product Marketing | · | Market Requirements Document |  | · | Pricing/ROI Research |  | · | Forecast Assumptions | · | Preliminary Benchmarks | · | Product introduction Plan |  | · | Usability Validation Report | · | Price Plan
|  | · | Needs and Tasks Analyses |  | · | Product Transition Strategy |  | · | Product Marketing Plan | [5 empty] | · | External Benchmarks
[5 empty] | · | Usability Investigation Plan |  | · | Seed Plan (Internal, External)
[8 empty] | · | Positioning Research
[8 empty] | · | Naming Plan
[8 empty] | · | Project Design Plan
[8 empty] | · | Usability Reports
| Project Management | · | Assign Project Leader |  | · | Project Plan |  | · | Manage Boundary Conditions
|  | · | Preliminary Project Plan |  | · | Create Schedule Prediction Accuracy |  | · | Manage Project Communications
|  | · | Create Team Wheel |  |  |  |  | · | Conduct Out of Bounds Review, if required
|  | · | Create Function Phase Matrix
| Hardware Engineering | · | Preliminary Engineering Requirements Specification (ERS) |  | · | ERS |  | · | HW Test Plan (EVT & Validation Phases) | · | PCB Design | · | 1st Tooled Parts |  | · | EMC Agency Submittals | · | Complete Production Release Documentation
|  | · | Industrial Design (ID) & Product Design (PD) Concept Exploration |  | · | ID/PD Concept Development |  | · | 1st Engineering BOM components specified | · | Build Plan Schedule | · | All Components Qualified |  | · | Life Test Performed, Reliability Goal Achieved |  | Agency Approvals Received (Safety, EMI)
[5 empty] | · | Preliminary Bill of Materials (BOM) |  | · | Configuration Mgmt Plan | · | Completed ASIC Qualification Plan | · | Engineering Release Documentation |  | · | AVL Complete | · | Engineering Support for Ramp
[5 empty] | · | ASIC Development/Tapeout |  | · | Localization Plan | · | ERS Update |  | ERS Finalized |  | · | PVL Complete | · | "2nd Source" Support
[8 empty] | · | ID/PD Layout, Strategy, Begin Detail Design | · | Early Test Results | · | Validation Test Plan Published |  | · | Production Parts | · | Continuation Engineering Plan
[8 empty] | · | User-centered Environmental Review | · | 1st EMC Testing | · | EVT Test Report |  | · | Validation Test Report
[8 empty] | · | EMC Plan Review | · | Early Reliability Testing | · | EMC Design Completed |  | · | Hardware Production Release Documentation
[8 empty] | · | Preliminary Reliability Goal Setting | · | Reliability Prediction Report |  |  |  | · | (end of phase)
| Software Engineering | · | Preliminary S/W Project Plan |  | · | S/W Requirements Analysis |  | · | S/W Project Plan Completed | · | Software Feature Implementation | · | Unit Level Testing |  | · | Final Candidate Software Release | · | Software Project Plan Post Mortem
[5 empty] | · | S/W Requirements Specification |  | · | S/W ERS Completed | · | Unit Level Testing | · | System Level Testing |  | · | Software Accepted as Final Quality | · | GM Accpetance Testing
[5 empty] | · | Preliminary Testing Impact Report |  | · | S/W Design Specification Completed | · | Feature Complete S/W Release | · | Beta Candidate Software Release |  | · | Software Accepted as GM Quality | · | Final Test Report
[5 empty] | · | Preliminary Software ERS |  | · | Test Plan & Schedule |  | (α Candidate) | · | Software Accepted as Beta Quality |  | · | Final Code Review
[5 empty] | · | Preliminary Design Specification |  | · | Formal System Level Quality Review | · | System Level Testing | · | QA Driven Software Changes |  | · | Final Component Software
[5 empty] | · | Testeing Responsibility Matrix Defined |  | · | Test Suites Developed | · | Software Accepted as α | · | β Candidate Component Software |  | · | Final Candidate Testing. Acceptance
[5 empty] | · | Localization Input |  | · | Software Release Strategy | · | CPU Specific Diagnostic SW Release | · | β Candidate Testing. Acceptance
[8 empty] | · | External Testing Proposal & Award | · | α Candidate Testing, Acceptance | · | General Diagnostic S/W Release
[12 empty] | · | Regress Test Diagnostic Software
| Operations |  |  |  | · | Supply Chain Design Recommendation |  | · | Design For Manufacturability (DFM) Input | · | Mfg Plan (Test, Process, etc.) | · | Transition Long Leadtime Materials |  | · | Production Process Validated | · | Outgoing Reliability & Quality Goals Achieved
[5 empty] | · | Material Acquisition Plan (MAP) |  | · | Supplier Management Strategy | · | Production Equipment Ordered |  | Management to Site(s) |  | · | Production Rev Test HW and SW Available | · | Achieve Time to Efficiency Goals
[5 empty] | · | Identify New Manufacuring Processes |  | · | Establish Global Ramp Plan | · | Localization Plan (Region/Site) | · | Manufacturing Test Available |  | · | Transition Materials management to Site(s) | · | Intro Requirements Achieved
[5 empty] | · | Initial Product Cost Projection |  |  |  | · | 1st Global Forecast Response | · | 1st Rev Test Equip SW Available |  | · | Materials Production Agreements | · | Begin Field Failure Feedback
[12 empty] | · | Process Metrics Established (yield & quality) |  | · | Standard Costs Established | · | Service Supplier Certification
[12 empty] | · | Final Global Ramp Plan & Intro Volumes |  | · | Final Cost, Price, and Marketing Numbers into Business | · | 3rd Party Repair Qualification
[12 empty] | · | Labeling Strategy Completed (UPC,multiple boxes, etc.) |  |  |  | · | Contract Mfg Process Qualification
[13 empty] | End of Life (EOL)/End of Product (EOP) Plan |  |  |  | · | End of Product (OP) "Last Time" Purchase Orders
| Service & Support |  |  |  | · | Customer Feedback |  | · | Design For Serviceablility (DFS) | · | Completed Service & Support Strategy | · | DFS Review/Approval |  | · | Finalize Warranty Model | · | Service Readiness
[5 empty] | · | Service & Support Impact Statement |  | · | Detailed Customer Feedback | · | End of Product (EOP) Impact |  |  |  | · | Tech Support Docs Complete |  | (Diags, Inventory, Tech Docs. & Comm)
[8 empty] | · | Initial Warranty Model | [7 empty] | · | Begin Problem Escalation, Resolution
[8 empty] | · | Service Requirements for Supplier D&D | [7 empty] | · | Warranty Updated w/Actuals
[8 empty] | · | Service Prototype & Seed Requirements
Function |  | Concept |  | Concept Review | Investigation |  | Product Proposal Review | Design | [5 empty] | Design Maturity Review | Validation |  | Production |  | Post Mortem Review
| Purpose of Phase | Exploring technical and market possibilities to meet customer needs. |  |  | Formulate boundary conditions of project; proof of concept; prototype or simulation completed |  |  | Engineering Validation Testing (EVT): Complete detailed product design conforming to specifications | [6 empty] | Design Validation Testing (DVT), Process Validation Testing (PVT): Prove Design Integrity and Manufacturing Process by testing units built in a production environment. |  | Satisfy customer demand, respond to customer problems, meet revenue commitments and achieve mfg goals
[8 empty] | Pre EVT |  | EVT 1.2. |  | EVT Final
| Product Marketing Bill | · | Market Requirements Document |  | · | Pricing/ROI Research |  | · | Forecast Assumptions | · | Preliminary Benchmarks | · | Product introduction Plan |  | · | Usability Validation Report | · | Price Plan
|  | · | Needs and Tasks Analyses |  | · | Product Transition Strategy |  | · | Product Marketing Plan | [5 empty] | · | External Benchmarks
[5 empty] | · | Usability Investigation Plan |  | · | Seed Plan (Internal, External)
[8 empty] | · | Positioning Research
[8 empty] | · | Naming Plan
[8 empty] | · | Project Design Plan
[8 empty] | · | Usability Reports
| Project Management Mei | · | Assign Project Leader |  | · | Project Plan |  | · | Manage Boundary Conditions | [5 empty] | · | Prepare Launch Plan | · | Conduct Project Post Mortem
|  | · | Preliminary Project Plan |  | · | Create Schedule Prediction Accuracy |  | · | Manage Project Communications
|  | · | Create Team Wheel |  |  |  |  | · | Conduct Out of Bounds Review, if required
|  | · | Create Function Phase Matrix
| Hardware Engineering Ravi | · | Preliminary Engineering Requirements Specification (ERS) |  | · | ERS |  | · | HW Test Plan (EVT & Validation Phases) | · | PCB Design | · | 1st Tooled Parts |  | · | EMC Agency Submittals | · | Complete Production Release Documentation
|  | · | Industrial Design (ID) & Product Design (PD) Concept Exploration |  | · | ID/PD Concept Development |  | · | 1st Engineering BOM components specified | · | Build Plan Schedule | · | All Components Qualified |  | · | Life Test Performed, Reliability Goal Achieved |  | Agency Approvals Received (Safety, EMI)
|  | · | Preliminar Hardware Plan |  | · | Preliminary Bill of Materials (BOM) |  | · | Configuration Mgmt Plan | · | ERS Update | · | Engineering Release Documentation |  | · | Approved Vendor List (AVL) Complete | · | Engineering Support for Ramp
[5 empty] | · | ASIC Development/Tapeout |  | · | Localization Plan | · | Early Test Results |  | ERS Finalized |  | · | PVL Complete | · | "2nd Source" Support
[8 empty] | · | ID/PD Layout, Strategy, Begin Detail Design | · | 1st EMC Testing | · | Validation Test Plan Published |  | · | Production Parts | · | Continuation Engineering Plan
[8 empty] | · | User-centered Environmental Review | · | Early Reliability Testing | · | EVT Test Report |  | · | Validation Test Report
[8 empty] | · | EMC Plan Review | · | Reliability Prediction Report | · | EMC Design Completed |  | · | Hardware Production Release Documentation
[8 empty] | · | Preliminary Reliability Goal Setting | [5 empty] | · | (end of phase)
| Software Engineering Julie | · | Preliminary Software Project Plan |  | · | S/W Requirements Analysis |  | · | S/W ERS Completed | · | Software Feature Implementation | · | Unit Level Testing |  | · | Final Candidate Software Release | · | Software Project Plan Post Mortem
[5 empty] | · | S/W Requirements Specification |  | · | S/W Design Specification Completed | · | Unit Level Testing | · | System Level Testing |  | · | Software Accepted as GM Quality | · | GM Accpetance Testing
[5 empty] | · | Preliminary Testing Impact Report |  | · | Test Plan & Schedule | · | Feature Complete S/W Release | · | Beta Candidate Software Release |  | · | Final Candidate Testing. Acceptance | · | Final Test Report
[5 empty] | · | Preliminary Software ERS |  | · | Formal System Level Quality Review |  | (α Candidate) | · | Software Accepted as Beta Quality
[5 empty] | · | Preliminary Design Specification |  | · | Test Suites Developed | · | System Level Testing | · | QA Driven Software Changes
[5 empty] | · | Testeing Responsibility Matrix Defined |  |  |  | · | Software Accepted as α | · | β Candidate Component Software
[5 empty] | · | Localization Input |  |  |  | · | α Candidate Testing, Acceptance | · | β Candidate Testing. Acceptance
[12 empty] | · | Regress Test Diagnostic Software
| WW Operations Jack |  |  |  | · | Material Acquisition Plan (MAP) |  | · | Design For Manufacturability (DFM) Input | · | Mfg Plan (Test, Process, etc.) | · | Transition Long Leadtime Materials |  | · | Production Process Validated | · | Outgoing Reliability & Quality Goals Achieved
[5 empty] | · | Identify New Manufacuring Processes |  | · | Supplier Management Strategy | · | Production Equipment Ordered |  | Management to Site(s) |  | · | Production Rev Test HW and SW Available | · | Achieve Time to Efficiency Goals
[5 empty] | · | Initial Product Cost Projection |  | · | Establish Global Ramp Plan | · | Localization Plan (Region/Site) | · | Manufacturing Test Available |  | · | Transition Materials management to Site(s) | · | Intro Requirements Achieved
[10 empty] | · | 1st Global Forecast Response | · | 1st Rev Test Equip SW Available |  | · | Materials Production Agreements | · | Begin Field Failure Feedback
[12 empty] | · | Process Metrics Established (yield & quality) |  | · | Standard Costs Established | · | Service Supplier Certification
[12 empty] | · | Final Global Ramp Plan & Intro Volumes |  | · | Final Cost, Price, and Marketing Numbers into Business | · | 3rd Party Repair Qualification
[12 empty] | · | Labeling Strategy Completed (UPC,multiple boxes, etc.) |  |  |  | · | Contract Mfg Process Qualification
[13 empty] | End of Life (EOL)/End of Product (EOP) Plan |  |  |  | · | End of Product (OP) "Last Time" Purchase Orders
| Service & Support Ben |  |  |  | · | Service & Support Impact Statement |  | · | Design For Serviceablility (DFS) | · | Completed Service & Support Strategy | · | DFS Review/Approval |  | · | Finalize Warranty Model | · | Service Readiness
[8 empty] | · | Detailed Customer Feedback | [5 empty] | · | Tech Support Docs Complete |  | (Diags, Inventory, Tech Docs. & Comm)
[8 empty] | · | Initial Warranty Model | [7 empty] | · | Begin Problem Escalation, Resolution
[8 empty] | · | Service Prototype & Seed Requirements | [7 empty] | · | Warranty Updated w/Actuals