## Instructions
What is a Lite Schedule Estimating Matrix?
• The spreadsheet-based tool guides the estimation of the amount of time a project takes in a given phase by using experience and the “critical few” key drivers that impact schedule.
• The matrix will predict the duration of each phase based on typical times and technical complexity.
• It helps experience program managers be more successful and helps communicate the schedule duration to management.
• The tool provides an alternative to the time-consuming bottom-up Gantt chart.
Which Business Problems Does the Tool Solve?
• Generates schedule estimates quickly.
Benefits:
• Improves the predictability of schedules since organization can learn from past schedules
• Reduces conflict between the team and management
• As companies become more efficient the value of the tool will grow over time
• Is a powerful method to capture institutional knowledge, especially given the turnover
• Establishes a common language and one consistent visual tool for schedule estimation
How to Apply the Tool:
• Input project phases vertically with historical range of months for each phase.
• Beneath each phase, list the key schedule drivers for each one.
• Second and third columns represent the historical range of the drivers (in number or percentage), from low to high.
• Fourth column estimates complexity of the project.
• Fifth column is open for comments.
• Identify key phases of your team’s project.
• List key components that drive the schedule beneath each phase and input historical range of the drivers.
• Estimate complexity of each driver.
• Enter durations for each phase based on your impressions of the relative complexity of the various drivers.

## Lite Schedule Estimating Matrix
Parametric Schedule Estimation Tool
[ Enter team name ] | [ Enter project name ]
Project characterization | Historical range |  | Estimate | Data, comments or explanation
1. Concept Phase | 1 | 12 | (Enter # months)
Key Drivers
Backup data - key variable elements affecting schedule
Number of new interfaces | 0 | 8 | Enter # new interfaces
Number of new processes that are part of the design | 0 | 5 | Enter # processes
Number of major new technologies required | 0 | 4 | Enter # technologies
Need vs. access to specific deep technical experience | 0 | 1 | Enter % of access
Relative complexity of getting applicable VOC on key concepts | 0 | 1 | Enter % complexity
Available resources planned vs. optimum resources for concurrent efforts | 0 | 1 | Enter % of optimum
2. Design Phase | 4 | 36 | (Enter # months)
Key Drivers
Backup data - key variable elements affecting schedule
Percentage of interfaces fully defined | 0 | 1 | Enter % defined
Complexity of system integration - delta from old to new interfaces | 0 | 12 | Enter # new integrations
Percentage of coupled vs. independent interfaces | 0 | 1 | Enter % highly coupled
Number of new vendors on the "critical path" | 0 | 10 | Enter # new vendors
Number of components with long lead times | 0 | 10 | Enter # LLT components
Number of iterations during development | 0 | 3 | Enter # iterations
Available resources planned vs. optimum resources for concurrent efforts | 0.4 | 1 | Enter % of optimum
3. Development Phase | 1 | 10 | (Enter # months)
Key Drivers
Backup data - key variable elements affecting schedule
Percentage of the specification with quantified test limits | 0.4 | 1 | Enter % of spec
Number of subsystems to be verified | 1 | 10 | Enter # subsystems
Number of verifications dependant on prior verifications | 0 | 20 | Enter # dependant
Number of iterations - due design feature creep | 1 | 8 | Enter # iterations
Available resources planned vs. optimum resources for concurrent efforts | 0.4 | 1 | Enter % of optimum
4. Testing Phase | 1 | 11 | (Enter # months)
Key Drivers
Backup data - key variable elements affecting schedule
Number of new processes requiring detailed test | 1 | 25 | Enter # of new processes
Relative completeness of design for manufacturability by this phase | 0 | 1 | Enter % of DFM done
Percentage of new vs. old use models | 0 | 1 | Enter % new uses
Relative amount of pre-work done with the customer | 0 | 1 | Enter % done
Number of test cases | 10 | 100 | Enter # cases
Relative availability of manufacturing bandwidth for low-rate builds | 0 | 1 | Enter availabilty %
Available resources planned vs. optimum resources for concurrent efforts | 0.4 | 1 | Enter % of optimum
5. Production readiness phase | 0 | 14 | (Enter # months)
Key Drivers
Backup data - key variable elements affecting schedule
Number of geographies targeted | 1 | 5 | Enter # geographies
Relative complexity of introduction (in the aggregate) | 0 | 1 | Enter complexity %
Interactions / dependencies with other introduction | 0 | 1 | Enter interaction %
Lag time after pilot introduction | 0 | 4 | Enter # months
Relative marketing strategy uncertainty | 0 | 1 | Enter uncertainty %
Available resources planned vs. optimum resources for concurrent efforts | 0.4 | 1 | Enter % of optimum
Characterization 6 {enter if applicable} |  |  | (Enter # months)
Characterization 7 {enter if applicable} |  |  | (Enter # months)
This project's estimated schedule (months) =
This project's actual schedule performance (months) =
Reflection metric: This project's schedule performance vs. estimate =
How to Apply the Tool: • Input project phases vertically with historical range of months for each phase. • Beneath each phase, list the key schedule drivers for each one.
• Second and third columns represent the historical range of the drivers (in number or percentage), from low to high. • Fourth column estimates complexity of the project.
• Fifth column is open for comments.
• Identify key phases of your team’s project.
• List key components that drive the schedule beneath each phase and input historical range of the drivers. • Estimate complexity of each driver.
• Enter durations for each phase based on your impressions of the relative complexity of the various drivers.