## Instructions
Project Escalation Map
What Is the Tool?
• A map that clarifies the boundaries and channels of decision-making in an organization.
• The tool displays a path for allowing decision-making at the lowest levels and minimizing the time it takes to escalate those that are outside the team’s span of control.
• The tool provides the team with a clear line of sight to who can resolve problems and how to make it happen.
Which Business Problems Does the Tool Solve?
• Effectively deals with struggles over decision-making when teams are stalled.
• Documents who decides what, given a specific set of conditions.
Benefits
• Saves time and energy by providing a clear escalation path for decision-making
• Educates new team members on how to make decisions quickly
• Minimizes delays in delivering products to market
• Drives accountability in the decision-making process
How to apply the tool
• Left column categorizes the type of decision.
• Middle column provides specific types of decision that map into the categories.
• Right column shows the path the escalation should follow from Individual Contributor to C-suite.
• Bottom section is the legend, identifying each organizational contributor and their decision authority.

## Project Escalation Map
Project Escalation Map
Project Escalation Map
Decision Category | Decision Type | Escalation Path
Product Features/Functionality | Feature | IC:FL:PM:CT/FD:BU:CMO
Staffing | Schedule, Cost | IC:FL:PM/FD:CT:BU
Change Management | Process | IC:PM:CT
Product Cost | Cost | IC:FL:PM:CT/FD:BU:CFO:COO
Legal | Legal | IC:FL:PM:GC
Customer Service | Schedule, Cost | IC:FL:PM:BU:CMO
Process Improvement | Schedule, Cost | IC:PM:PMO
Project Escalation Map Legend
Legend | Organizational Contributor | Decision Authority
IC | Functional Individual Contributor | Functional Execution
FL | Functional Lead | Functional Delivery
PM | Project Manager | Project Delivery
CT | Cross-Functional Project Team | Cross-Functional Execution
FD | Functional Director (or VP) | Functional Budget
BU | Business Unit Lead | BU Delivery
GC | General Counsel | Legal Compliance
PMO | Project Management Office (or PM Leadership) | Cross-Project Delivery
CMO | Chief Marketing Officer | Customer Experience
COO | Chief Operating Officer | Corporate Execution
CFO | Chief Financial Officer | Corporate Financial Performance
CEO | Chief Executive Officer | Corporate Delivery
How to Apply the Tool:
• Left column categorizes the type of decision.
• Middle column provides specific types of decision that map into the categories.
• Right column shows the path the escalation should follow from Individual Contributor to C-suite.
• Bottom section is the legend, identifying each organizational contributor and their decision authority.