## Instructions
Requirements Management Matrix
What Is the Tool?
The tool uses two charts to Apply agile development concepts to product definition.
The “Kanban” process creatively and innovatively defines your inventory of unfinished requirements and tracks them.
New use cases can be added as new scenarios are envisioned.
The accompanying burn down chart gives team members a sense of progress and helps them quickly focus on incomplete quality definitions.
Which Business Problems Does the Tool Solve?
Helps break the myth that you cannot have both innovation and speed at the same time.
Facilitates innovative requirements and tracks them.
Helps organizations develop difficult platform programs quickly and creates a common vision for the product.
Benefits
This methodology can help you create compelling product definitions
It increases definition speed due to the tight loop of iteration between development and management
Quality of the definition is better because we have the collective intelligence of the organization
How to apply the tool
First column in top chart describes known but undefined requirements.
Second column lists requirements that have been discussed but not finished.
Last column represents requirements that have been agreed upon and fully defined.
In the burn down chart (3rd tab), the vertical axis is the number of undefined requirements.
Horizontal axis represents the session number and shows progression on outstanding requirements.
Define your product (e.g., new HR system) .
Add project requirements at differing stages of definition.
Create three addition snapshot charts showing the movement of requirements over time.
Plot the progression on the burn down chart.

## Requirements Management Matrix
Requirements Management Matrix
Requirements Management Matrix (After First Session)
Candidate | In Process | Defined
1. 360 Feedback | 1. Union/Non-Union Compatible | 1. SAAS
2. Salary Benchmarks | 2. Pre-populated Feedback Sentences | 2. Corrective Action
3. Calibration | 3. Tracking of last year's performance
4. Goal Setting
5. Performance Improvement
How to Apply the Tool:
• First column in top chart describes known but undefined requirements.
• Second column lists requirements that have been discussed but not finished.
• Last column represents requirements that have been agreed upon and fully defined.

## Burn Down Chart
Burn Down Chart Outstanding Requirements
Session | Target | Actual
Starting | 10 | 10
Session #1 | 7 | 8
Session #2 | 4 | 5
Session #3 | 0 | 1
Session #4 | 0 | 0
How to Apply the Tool:
• First column in top chart describes known but undefined requirements.
• Second column lists requirements that have been discussed but not finished.
• Last column represents requirements that have been agreed upon and fully defined.
• In the burn down chart below, the vertical axis is the number of undefined requirements.
• Horizontal axis represents the session number and shows progression on outstanding requirements.
• Define your product (e.g., new HR system) .
• Add project requirements at differing stages of definition.
• Create three addition snapshot charts showing the movement of requirements over time.
• Plot the progression on the burn down chart.