## Instructions
Risk Management Matrix
What is a Risk Management Matrix?
• The matrix is an elegant way to anticipate, manage, and mitigate product development risks.
• The tool lists various risks, their overall impact, and an action plan if risk values are exceeded.
• Creation of the table should take place during the first 10-15% of a project’s duration.
• You can update and modify the tool on an ongoing basis, adding new metrics as they occur and removing risks that were eliminated.
Which Business Problems Does the Tool Solve?
• Innovation brings with it additional risks which can still be managed by the team on its own.
• Helps improve project execution because it can help the team anticipate, prevent, and mitigate risks.
Benefits:
• You can identify risks before they occur
• There is a reduction of risk impact due to early detection
• You will have quantitative metrics that help clarify when to act on a risk item
• Accelerated actions will happen because of the clear thresholds and the agreement to follow the process
How to Apply the Tool:
• Project risks are listed on left side.
• Impact column with score of 1 (indicating zero risk) to 10 (indicating greatest risk).
• Likelihood column with score of 1 (indicating zero risk) to 10 (indicating greatest risk).
• Metric column is the measurable quantity associated with the risk.
• Threshold column indicates the value that must be hit by the time product is shipped.
• Date column indicates time by which performance must equal or exceed threshold value.
• Action Plan column gives a detailed description of the high-level objectives of an action plan.
• Define the top risks in your product development project.
• Assign impact, likelihood, metric, threshold and current values for each from 1 (zero risk) to 10 (greatest risk).
• Define the date by which performance must equal or exceed threshold value.
• Describe in detail the objectives of action plan for each risk.

## Risk Management Matrix
Risk Management Matrix
Risk Management Matrix
Status | Risk | Impact | Likelihood | Metric | Threshold | Current Value | Date | Action Plan
| Global team does not communicate frequently enough. Want to keep weekly communication high. | 4 | 7 | Meetings per week | 2 | 2.5 | Current | Invoke team's elevation plan, purchase videoconferencing systems, change incentives
| Data captured on long forms from online interaction sessions must not be lost if user gets error message or returns to screen. | 6 | 6 | % Data Lost | 10% | 25% | Q4 FY '13 | Design review current forms layout, bring in Expert Co. consulting firm, change staff balance
| Server must respond to users rapidly under fairly high loads - expect page to be updated way under a second. | 7 | 7 | Ms at 1000 Users | 259 | 1000 | Q4 FY '13 | Add architect and create tiger team with system optimization experience
| Financial partner cooperation is critical to this household finance program, and we need to have a sufficient number at launch. | 4 | 6 | Instructions | 1000 | 247 | Q4 FY '13 | Increase business development staff, change incentive compensation, add external business development firm
| Mobile operating system support must be in place at the same time as launching the desktop version. | 5 | 6 | On Time | Q4 FY '14 | Q4 FY '14 | Current | Track schedule prediction accuracy. If slip then recruit internal team from Vietnam (permission already granted)
How to Apply the Tool:
• Project risks are listed on left side.
• Impact column with score of 1 (indicating zero risk) to 10 (indicating greatest risk).
• Likelihood column with score of 1 (indicating zero risk) to 10 (indicating greatest risk).
• Metric column is the measurable quantity associated with the risk.
• Threshold column indicates the value that must be hit by the time product is shipped.
• Date column indicates time by which performance must equal or exceed threshold value.
• Action Plan column gives a detailed description of the high-level objectives of an action plan.
• Define the top risks in your product development project.
• Assign impact, likelihood, metric, threshold and current values for each from 1(zero risk) to 10 (greatest risk).
• Define the date by which performance must equal or exceed threshold value.
• Describe in detail the objectives of action plan for each risk.