## Instructions
Root Cause Diagram
What Is the Tool?
The Root Cause Diagram is a framework to support the discovery of the ultimate cause of an outcome.
• Also known as the fishbone diagram or Ishikawa diagram, it is the diagram representation of the outcome of a method where individuals or groups systematically attempt to determine the set of the most fundamental, detailed, specific, and fact-based causes that led to a specific outcome.
The application of the Root Cause Diagram is flexible and straightforward, and you can accomplish it in two one-hour sessions.
Which Business Problems Does the Tool Solve?
This tool facilitates fact-based decision making and evidence-based management.
The fishbone diagram is a nice way of diagramming the discussion of an exercise to determine root causes, but it is difficult to share after the meetings, or real time in a distributed meeting.
By using a spreadsheet tool, it facilitates the use of root cause documentation because it is trivial to share and archive.
Benefits
• Saves time because the team does not repeat mistakes. This tool ensures that the team will manage the actual root causes, not just the symptoms.
• Minimizes re-evaluation because the team does the formal exercise once at the beginning of a project.
• Generates consensus because it is a cross-functional effort, and all the participants collaborate on the key takeaways of the process.
• Prevents swirling changes in direction because it drives thoughtful and fact-based decision-making.
How to apply the tool
• The first step in this process is identifying the problem and creating a clear problem statement.
• The second step is to list out standard categories for the root causes of the problem statement.
• The third step is to then ask why each category led to the outcome. You repeat this process (also known as the 5 Whys) up to five times. Use the Root Cause Diagram spreadsheet to log these answers.
• The fourth step is to come to an agreement on the most likely root cause (or causes).
• The best way to implement the Root Cause Diagram is with a cross-functional team and a facilitator.
• You can carry out the first session, covering steps one through three, in an hour if everyone is prepared.
• You can conduct the fourth step in a second meeting since it involves data collection and analysis.

## Root Cause Diagram
Root Cause Diagram
Problem Statement: “What were the root causes of the long test phase in project Jupiter?”
Root Cause Diagram
Category | Why #1 | Why #2 | Why #3
Engineering | Lack of unit testing
Lack of training
Lack of process steps
Management does not support process
Unclear exit criteria
Unclear functional specification
Marketing | Changing product definition
Software Quality Assurance | Insufficient staff
Manager left 1/2 way through test phase
Low morale
Overworked
Underappreciated
Insufficient Automation
Budget does not allow for automation effort
Lack of comprehensive test plan
Quality joins team at feature-complete milestone
Process | Quality joins team after design phase
Process is not enforced so engineering does not follow procedures
Executives change features at last minute
Release criteria is not clear
Technology | Lack of test automation
Lack of budget
Lack of top management support
Bug tracking system insufficient
How to Apply the Tool:
• The first step in this process is identifying the problem and creating a clear problem statement.
• The second step is to list out standard categories for the root causes of the problem statement.
• The third step is to then ask why each category led to the outcome. You repeat this process (also known as the 5 Whys) up to five times. Use the Root Cause Diagram spreadsheet to log these answers.
• The fourth step is to come to an agreement on the most likely root cause (or causes).
• The best way to implement the Root Cause Diagram is with a cross-functional team and a facilitator.
• You can carry out the first session, covering steps one through three, in an hour if everyone is prepared.
• You can conduct the fourth step in a second meeting since it involves data collection and analysis.