## Instructions
What is the Schedule Prediction Accuracy Tool?
• The scatter chart maintains a record of the original plan and provides an early warning when a project fails to hit its expected schedule.
• The tool highlights how a project's milestones are changing over time.
• Project teams can use the tool to anticipate problems before they occur and intervene before projects fall behind.
• The tool provides a framework for conducting a well-focused root cause analysis.
What Business Problems Does the Tool Solve?
• Helps predict problems before they occur.
• Accelerates time-to-market by the early detection and elimination of project risks
Benefits:
• Serves as an early warning sign to prevent projects from going off track and gives the team the best chance of avoiding disasters.
• Is a tactically straightforward, but strategically powerful tool that drives better decisions faster.
• Provides a robust visualization of the entire project over time, with a visual emphasis on significant changes in schedule.
• Identifies back-end milestone compression to drive risk reduction earlier into the process.
• Increases accountability for the program manager.
• Eliminates the schedule gaming.
How to Apply the Tool
Use the below instructions to create your own Schedule Prediction using the Sample on the 'Schedule Predictability Chart' and 'Schedule Prediction Dates' tabs as a starting point.
Step 1: Horizontal "Y" axis represents the predicted date when the project will achieve a milestone
Step 2: Vertical "X" axis represents the current prediction for the milestone
Step 3: Milestones for a project with no schedule impacts will appear over time as a horizontal line
Step 4: Anticipated schedule changes result in the upward slope of line
Step 5: Diagonal "finish line" represents when project should reach each milestone based on initial plan
Step 6: Chart should be updated on a regular basis (typically weekly) for best accuracy
Note: This tools applies the Excel straight-line scatter plot formula. When a schedule is perfectly executed, all milestone lines will be horizontal. When a milestone slip occurs, it will be visible in a change to the slope of the line.
• Use the 'Schedule Predictability Chart' and 'Schedule Prediction Dates' tabs to create the Schedule Predictability Accuracy chart
• Identify key project milestones
• Plot the predicted completion dates for each milestone
• Introduce significant completion date changes for selected milestones
• Identify causes for delays

## Schedule Predictability Chart
Note: This tools applies the Excel straight-line scatter plot formula.
When a schedule is perfectly executed, all milestone lines will be horizontal. When a milestone slip occurs, it will be visible in a change to the slope of the line.
How to Apply the Tool:
Step 1: Horizontal "Y" axis represents the predicted date when the project will achieve a milestone
Step 2: Vertical "Y" axis represents the current prediction for milestone
Step 3: Milestones for a project with no schedule impacts will appear over time as a horizontal line
Step 4: Anticipated schedule changes results in the upward slope line
Step 5: Diagonal "finish line" represents when project should reach each milestone based on initial plan
Step 6: Chart should be updated on a regular basis (typically weekly) for best accuracy
• Use the 'Schedule Predictability Chart' and 'Schedule Prediction Dates' tabs to create the Schedule Predictability Accuracy Chart
• Identify key project milestones
• Plot the predicted completion dates for each milestone
• Introduce significant completion date chages for selected milestones
• Identify causes for delays

## Schedule Prediction Dates
Project Name:
Date of schedule | Finish Line | Alpha Finished | Beta Finished | System Live
2010-09-01 | 2010-09-01 | 2010-09-17 | 2010-11-15 | 2010-12-30
2010-09-08 | 2010-09-08 | 2010-09-17 | 2010-11-15 | 2010-12-30
2010-09-15 | 2010-09-15 | 2010-09-17 | 2010-11-15 | 2010-12-30
2010-09-22 | 2010-09-22 | 2010-09-25 | 2010-11-15 | 2010-12-30
2010-09-29 | 2010-09-29 | 2010-09-25 | 2010-11-15 | 2010-12-30 | 40426
2010-10-06 | 2010-10-06 |  | 2010-11-15 | 2010-12-30 | 40555
2010-10-13 | 2010-10-13 |  | 2010-11-15 | 2010-12-30
2010-10-20 | 2010-10-20 |  | 2010-11-15 | 2010-12-30
2010-10-27 | 2010-10-27 |  | 2010-11-15 | 2010-12-30
2010-11-03 | 2010-11-03 |  | 2010-11-30 | 2010-12-30
2010-11-10 | 2010-11-10 |  | 2010-11-30 | 2010-12-30
2010-11-17 | 2010-11-17 |  | 2010-11-30 | 2010-12-30
2010-11-24 | 2010-11-24 |  | 2010-11-30 | 2011-01-05
2010-12-01 | 2010-12-01 |  | 2010-11-30 | 2011-01-05
2010-12-08 | 2010-12-08 |  |  | 2011-01-05
2010-12-15 | 2010-12-15 |  |  | 2011-01-05
2010-12-22 | 2010-12-22 |  |  | 2011-01-05
2010-12-29 | 2010-12-29 |  |  | 2011-01-05
2011-01-05 | 2011-01-05 |  |  | 2011-01-05
Place new dates in blue cells
If the date slips, extend the columns so that they intercept the finish line
Numbers in cells G38 and G39
These numbers define the range of dates in the x- and y-axes.
They are set when editing the axes in the chart. (highlight axis in chart ==> Format Axis ==>Scale)
-73
Formulas:
Finish Line = [Date of schedule]
Date of schedule = [Date of schedule, row above]+7
Note on D12: NEIVERT: Set "first demo" as Mid CY08 but this is not the same as RC so no data used
Note on E12: NEIVERT: Slide 2 No end date established Slide 3 Set GA date between FY09 and FY10, so picked the date May 1st 2009
Note on D13: NEIVERT: Slide 7 Q1 CY09 "first release" midpoint of this is Feb 15th 2009 Slide 8 repeats Q1 CY09
Note on E13: NEIVERT slide 8 shows May st 2009 visually
Note on D14: NEIVERT: Slide 12 March 2009 Slide 13 repeats march 2009 Picked middle day
Note on E14: NEIVERT slide 13 shows May st 2009 visually
Note on D15: NEIVERT: Slide 27 March 2009 Slide 28 repeats March 2009 Picked middle day
Note on E15: NEIVERT: Slide 18 show GA between FY 2009 and FY 2010 so picked May 1, 2009
Note on D16: NEIVERT: Slide 22 March 2009 Slide 23 repeats March 2009 Picked middle day
Note on E16: NEIVERT: Slide 23 show GA between FY 2009 and FY 2010 so picked May 1, 2009
Note on D17: NEIVERT: Slide 27 March 2009 Slide 28 repeats March 2009 Picked middle day
Note on E17: NEIVERT: Slide 28 show GA between FY 2009 and FY 2010 so picked May 1, 2009
Note on D18: NEIVERT: Slide 32 RC1 target April 2009 Slide 33 repeats
Note on E18: NEIVERT: Slide 33 show GA between FY 2009 and FY 2010 so picked May 1, 2009
Note on D19: NEIVERT: Slide 37 RC1 target April 2009 Slide 38 repeats
Note on E19: NEIVERT: Slide 38 show GA between FY 2009 and FY 2010 so picked May 1, 2009
Note on D20: NEIVERT: Slide 43 RC1 target April 2009 Slide 44 repeats
Note on E20: NEIVERT: Slide 44 show GA between FY 2009 and FY 2010 so picked May 1, 2009
Note on D21: NEIVERT: Slide 49 Noted current tracking date as ">6/29/09" slide 50 notes Slide 51 agrees FCS is Q2FY09
Note on E21: NEIVERT: removed from slides or listed as N/A
Note on D22: NEIVERT: slide 54 "May/June 2009" picked the mdidle date Slide 56 "~6/29/09" slide 58 "Q2CY09"
Note on E22: NEIVERT: Removed from slides, or listed as N/A
Note on D23: NEIVERT: Slide 60 indicates >6/29/09 Slide 61 indicates RC1 is ">4/17/09 slide 64 "Q2CY09"
Note on E23: NEIVERT: Removed from slides, or listed as N/A