## Instructions
What is a Staffing Ratio Matrix?
• The straightforward matrix looks at staffing ratios to help managers execute effectively.
• It summarizes all projects, charting them against key functions on a cross-functional team.
• The tool provides insight into functional bottlenecks and overloaded individuals to help restore balance to the team.
Which Business Problems Does the Tool Solve?
• It ensures you will have skilled individuals working on key deliverables.
• You can solve imbalance problems with no increase in budget.
• By transferring engineers to different functions, you can improve the balance and create a better environment for employees who want to expand their experience.
Benefits:
• Is a quick way to cut through politics whenever a manager asks for more people
• Makes engineering much more efficient by eliminating functional shortages
• Improves project outcomes because tasks are assigned to qualified workers
How to Apply the Tool:
• First column identifies the project name.
• Second column indicates the number of development engineers working on the project.
• Third column names the project manager.
• Fourth column summarizes the number of projects per project manager.
• Columns 3 & 4 are repeated for the critical functions.
• Last two rows at bottom of matrix summarize the workload ratio and best in class ratio.
• Create a Staffing Ratio Matrix with your team
• List all projects in your organization
• Identify their key functions (typically engineering, product management, project management, user experience and quality).
• Name the team member working on each project.
• Summarize the information and compare the average ratios to benchmarks.
• Identify the overtaxed individuals and address which functions could be redeployed to improve the balance.

## Staffing Ratio Matrix
Staffing Ratio Matrix
Project | Engineers | Product Management | Ratio | Project Management | Ratio | User Experience | Ratio | Quality | Ratio
1. Blackbeard | 32 | Fred |  | Bob |  | Sarah | Medium | Andy
2. Bluetooth | 22 | Fred |  | Bob |  | Sarah | Medium | Andy | 2
3. Redhead | 18 | Fred |  | Bob |  | Sarah |  | John
4. Silverfox | 25 | Fred |  | Bob | 4 | Sarah |  | John | 2
5. White Prince | 22 | Fred |  | Mary |  | Sarah |  | Bill | 1
6. White Queen | 13 | Fred |  | Mary |  | Sarah |  | Jill
7. Mini Queen | 4 | Fred | 7 | Mary |  | Sarah |  | Jill
8. Queen Three | 11 | Phil |  | Mary | 4 | Sarah | 8 | Jill | 3
9. Bambi | 13 | Phil |  | Susan |  | Mindy |  | June
10. BamBam | 8 | Phil |  | Susan |  | Mindy |  | June
11. Fred | 12 | Phil |  | Susan | 3 | Mindy |  | June | 3
12. Martha | 5 | Phil |  | Flo |  | Mindy |  | Janet
13. Martha II | 7 | Phil |  | Flo |  | Mindy |  | Janet
14. Martha III | 5 | Phil |  | Flo |  | Mindy |  | Janet
15. Martha Junior | 4 | Phil | 8 | Flo | 4 | Mindy | 7 | Janet | 4
Average Ratio |  | Enj/Proj | 7.5 | Proj/PdM | 3.75 | Proj/PjM | 7.5 | Proj/Qual | 2.5
Best Practice |  |  | 1 |  | 1.5 |  | 4 |  | 1.5
How to Apply the Tool:
• First column identifies the project name. • Second column indicates the number of development engineers working on the project. • Third column names the project manager. • Fourth column summarizes the number of projects per project manager. • Columns 3 & 4 are repeated for the critical functions. • Last two rows at bottom of matrix summarize the workload ratio and best in class ratio. • Create a Staffing Ratio Matrix with your team • List all projects in your organization • Identify their key functions (typically engineering, product management, project management, user experience and quality). • Name the team member working on each project. • Summarize the information and compare the average ratios to benchmarks. • Identify the overtaxed individuals and address which functions could be redeployed to improve the balance.