## Slide 1
What is a Team PERT Chart?
• The diagram is used by the group to generate a schedule and help reduce time to market.
• The tool supports the trend toward more collaborative team involvement.
• Creating the chart using the team-based method gives you cross-functional buy-in and a schedule your team can support.
Which Business Problems Does the Tool Solve?
• Reduces time to market by forcing team to understand what is on the critical path and helps them reduce its duration.
• Empowers teams to create their own schedule because they have been delegated more authority.
• Increases predictability by getting all the functional inputs into key milestones, ensuring that your team doesn’t inadvertently omit key tasks.
Benefits:
• Focuses on the critical path to reduce the overall cycle time
• Is a fast method to create schedules
• Ensures cross-functional alignment and buy-in to the tasks and timelines
• Provides accurate estimates of the time needed to complete each task
• Eliminates the need for complex and expensive project management software
How to Apply the Tool:
• Shaded boxes represent stages between Market Requirements Document (MRD) and Concept Review.
• Numbers at bottom of each box are the times needed to complete the tasks (in weeks). (First number is the optimistic estimate; middle number is typical duration; last number is pessimistic estimate – refer to separate table)
• Critical path is identified by the larger gray dotted line.
• Create a Team PERT Chart with your team
• Identify key tasks between MRD and Concept Review for your project and plot the steps to get from one milestone to another.
• Ask each team member to determine the time needed to complete each task (optimistic, typical, pessimistic).
• Summarize the duration estimates, checking those that look out of line.
• Make sure no key tasks were omitted.
• Draw the critical path by making it darker than the other arrows connecting the tasks.
• Brainstorm how to shorten the critical path and integrate solutions into the diagram.

## Slide 2
How to Apply the Tool:
• Shaded boxes represent stages between Market Requirements Document (MRD) and Concept Review.
• Numbers at bottom of each box are the times needed to complete the tasks (in weeks). (First number is the optimistic estimate; middle number is typical duration; last number is pessimistic estimate – refer to separate table)
• Critical path is identified by the larger gray dotted line.
• Create a Team PERT Chart with your team (this is best done on a whiteboard with Post-It Notes)
• Identify key tasks between MRD and Concept Review for your project and plot the steps to get from one milestone to another.
• Ask each team member to determine the time needed to complete each task (optimistic, typical, pessimistic).
• Summarize the duration estimates, checking those that look out of line.
• Make sure no key tasks were omitted.
• Draw the critical path by making it darker than the other arrows connecting the tasks.
• Brainstorm how to shorten the critical path and integrate solutions into the diagram.